## Sheet1
| Paragraph text | Start index | Page nr | Locations | Disasters | Dates | Victims
0 |  | 0 | 1
1 | (This document is the property of the Government of the Republic of Zambia) | 1 | 1
2 | Republic of Zambia | 79 | 1
3 | PREPARED BY: DMMU/PARTNERS LUSAKA | 100 | 1 | Lusaka
4 | FLOODS RECOVERY ACTION PLAN | 138 | 1 |  | flood
5 | June 2009 TABLE OF CONTENTS Acronyms iv EXECUTIVE SUMMARY v 1. INTRODUCTION 1 2.0. SCALE OF THE PROBLEM 2 3.0 RATIONALE FOR THE IMPLEMENTATION OF RECOMMENDED INTERVENTIONS 2 4.0 GENERAL RESPONSE STRATEGY 3 5.0 REQUIRED INTERVENTIONS 3 6.0 IMPLEMENTATION PLAN 6 6.1 Current level of response 6 6.2 Scaling Up 6 7.0 ROLES AND RESPONSIBILITIES 6 8.0 TIME FRAME 7 9.0 REPORTING ARRANGEMENTS 7 10.0 COORDINATION 7 11.0 MONITORING AND EVALUATION 8 ANNEXES 12 Annex 1: EDUCATION 12 Annex 2: HEALTH 22 Annex 3: NUTRITION 28 Annex 4: HUMAN SETTLEMENT AND SHELTER 30 Annex: 5. INFRASTRUCTURE 35 Annex 6: SOCIAL PROTECTION 42 Annex 7: WATER AND SANITATION 46 Annex: 8: AGRICULTURE AND FOOD SECURITY 52 | 168 | 2 |  | water | June 2009 T
6 | 2 Table of Tables Table 1: Summary of Financial Requirements for Sectors vi Table 2: Sector by Activity 4 Table 3: Monitoring And Evaluation Indicator 9 Table 4: Education Activity Budget 13 Table 5: Education Implementing Schedule 21 Table 6: Health Activity Schedule 23 Table 7: Essential Drugs and Supplies 26 Table 8: Nutrition Activity Schedule 29 Table 9: Human Settlement and Shelter Activity matrix and Budget 33 Table 10: Human Settlement and Shelter Schedule 34 Table 11: Summary of Number Of Structures Assessed 37 Table 12: Infrastructure Activity Costs per Province 38 Table 13: Infrastructure Activity Matrix 39 Table 14: Infrastructure Priority Cost List Per Province 40 Table 15 : Infrastructure Implementation Schedule 41 Table 16: Social Protection Activity Budget 44 Table 17: Social Protection Implementation Schedule 2009 - 2010 45 Table 18: Water and Sanitation Activity Budget and Schedule 2009 – 2010 (Requirements by District) 48 Table 19: Water and Sanitation Activity Schedule 51 Table 20: Agriculture Activity Schedule 54 Table 21: Estimated Input Requirements to Enable Targeted Households cultivate 1 Lima of Maize for Off Season Crop production 55 Table 22: Food Relief Activity Matrix 59 | 889 | 3 |  | water, water | 2009, 2010 | household, households
7 | Acronyms | 2139 | 4
8 | DDMC District Disaster Management Committee DMMU Disaster Management and Mitigation Unit ITNs Insecticides Treated Nets IOM International Organisation for Migration MCDSS Ministry of Community Development and Social services MoE Ministry of Education MEWD Ministry of Energy and water Development MoH Ministry of Health NGO Non Governmental Organization RDA Road Development Agency UN ZA | 2153 | 4 |  | water
9 | United Nations Zambia Army ZMD Zambia Meteorological Department ZNS Zambia National Service ZVAC Zambia Vulnerability Assessment Committee | 2563 | 4
10 | EXECUTIVE SUMMARY | 2711 | 5
11 | Following recommendations from the 2009 rapid assessment, the Zambia Vulnerability Assessment Committee (ZVAC) undertook the In-Depth Vulnerability and Needs Assessment in twenty (20) districts. The assessment report made recommendations necessary to mitigate the effects of floods and /or water logging in the affected districts. | 2734 | 5 |  | water, flood | 2009
12 | In order to ensure speedy implementation of these recommendations, it became necessary to translate the recommendations into a Recovery Action Plan with specific activities and costing. | 3071 | 5
13 | The document starts with an introduction that discusses the structure and management of the Recovery Action Plan. The required sector specific interventions and costing are then discussed focusing on Education, Health, Nutrition, Infrastructure, Human Settlement and Shelter, Water and Sanitation, Agriculture and Food Security. | 3261 | 5 |  | water
14 | It is important to note that recommended interventions reflect sectoral needs in short, medium and long-term perspectives. The financial requirements per sector are also discussed. | 3596 | 5
15 | v The summary of the financial requirements per sector is reflected in the table below: | 3781 | 6
16 | Table 1: Summary of Financial Requirements for Sectors | 3876 | 6
17 | Name of Sector Education Health Nutrition Infrastructure Human Settlement and Shelter Social Protection Water and Sanitation Agriculture and Food Security 10% Contingency | 3933 | 6 |  | water
18 | Grand Total No. of activities Net Financial Requirements Net Financial Requirements (ZMK) (US$) @ K5,000 2 3 4 | 4118 | 6
19 | 4 3 3 | 4243 | 6
20 | 6 | 4253 | 6
21 | 672,000,000.00 134,400.00 913,276,775.00 182,655.36 | 4257 | 6
22 | 3,873,765,850.60 774,753.17 | 4314 | 6
23 | 62,644,544,746.00 12,528,908.95 | 4345 | 6
24 | 662,920,000.00 132,584.00 | 4380 | 6
25 | 6,725,000,000.00 1,345,000.00 8,379,843,031.00 1,675,968.61 | 4409 | 6
26 | 22,805,937,247.00 4,561,187.45 10,667,728,764.96 2,133,545.75 | 4474 | 6
27 | 117,345,016,414.56 23,469,003.72 | 4541 | 6
28 | The Implementation of the action plan is to be done with full participation of all stakeholders such as relevant Government agencies, donors, UN System, private sector and NGOs. The NGOs in conjunction with the district and satellite disaster management committees will be the front line implementers at the district level. The timeframe for the implementation of interventions is projected to be twelve (12) months beginning in July 2009. The Disaster Management and Mitigation Unit (DMMU) will spearhead coordination and monitoring of the implementation of the action plan with the support of the | 4577 | 6 |  |  | July 2009
29 | vi core coordination team, drawing membership from Government, UN, and NGO agencies. Monitoring and evaluation of the Recovery Action Plan will be based on sector specific performance indicators that form part of this action plan document. | 5185 | 7
30 | vii 1. INTRODUCTION | 5434 | 8
31 | The beginning of the 2008/9 rainy season was described by the Zambia Meteorological Department (ZMD) as normal with the rains having started early in most parts of the country apart from the extreme eastern parts of the country (Lundazi, Chama and Isoka). However, as the season progressed it was characterised by wide spread heavy rains resulting in floods in some parts of the country. The floods, which were characterised by wide spread flash flooding mostly in low lying areas of the country (i.e. valleys), negatively impacted the key sectors of the economy. The degree of the impact varied from sector to sector. | 5460 | 8 | Lundazi, Chama, Isoka | extreme, flood, flood, flood, flash, rain, rain, rain | 2008/9
32 | In view of the above, the Zambia Vulnerability Assessment Committee (ZVAC) undertook a Multi-sectoral In-depth Assessment in twenty (20) districts. The assessment was aimed at determining the extent and effects of the 2008/9 floods and/or water logging on various sectors of the economy. The provinces and districts where the assessments were conducted included Central Province (Kapiri-Mposhi and Serenje), Eastern Province (Mambwe), Luapula Province (Kawambwa), Northern Province (Mpika, Mungwi and Mporokoso), North-Western Province (Chavuma, Kabompo, Kasempa, Mufumbwe, Mwinilunga, Zambezi) Western Province( Kalabo, Kaoma, Lukulu, Mongu, Senanga, Shangombo, Sesheke) To ensure a speedy and coordinated response, the Government of the Republic of Zambia has provided a general framework within which all stakeholders will undertake all interventions related to floods. The plan defines the scale of the problem and the rationale for the implementation of the recommended interventions. It brings out the general response strategy and outlines sector based interventions in short and medium to long-term perspectives. Implementation, reporting, monitoring and coordination arrangements are also spelt out. | 6088 | 8 | Serenje, Mambwe, Kawambwa, Lunga, Mpika, Chavuma, Kabompo, Kasempa, Mufumbwe, Mwinilunga, Zambezi, Mporokoso, Mungwi, Kalabo, Kaoma, Lukulu, Mongu, Senanga, Sesheke | water, flood, flood | 2008/9
33 | 1 2.0. SCALE OF THE PROBLEM The country has experienced floods for three consecutive seasons which have resulted in damage to Infrastructure mainly roads, culverts and bridges as well as Crops. These floods and/or water logging have generally exposed the affected Population to the risk of outbreak of waterborne diseases and increased the likelihood of animal disease incidences to rise. The damage to crops created food insecurity problems in the districts affected in the five (5) provinces although there was a marginal increase in crop production. In order to mitigate the impact of the floods, Government will need to implement short to medium and long-term interventions in all the eight (8) sectors identified to have been affected. | 7316 | 9 |  | disease, disease, water, water, disease, disease, disease, disease, flood, flood, flood
34 | 3.0. RATIONALE FOR THE IMPLEMENTATION OF RECOMMENDED INTERVENTIONS | 8072 | 9
35 | The 2008/09 rainfall season was characterised with wide spread heavy rains in most parts of the country with wide spread flash flooding mostly in low lying areas of the country (i.e. valleys) that resulted into adverse impacts on different key economic sectors such Agriculture and Food Security, Education, Health and Nutrition, Infrastructure, human Habitations Water and Sanitation in five (5) provinces of the country. | 8142 | 9 |  | water, flood, flash, rain, rain | 2008/09
36 | The Government should as a matter of urgency address the negative impact of the floods by implementing sector specific interventions which range from short term needs to those that seek to address medium to long term needs. The implementation of the recommended interventions will help open up places that were cut off due to damage to infrastructure, thus effectively restoring the movement of people. The interventions will further help mitigate other negative effects in the identified sectors such as prevention of water borne diseases, maintain economic viability and reduce if not prevent increase in the levels of malnutrition among affected communities through provision of relief. | 8572 | 9 |  | disease, water, disease, disease, flood
37 | 2 | 9272 | 10
38 | 4.0 GENERAL RESPONSE STRATEGY | 9279 | 10
39 | The government’s strategy is to mobilize all available human, financial and material resources and redirect these to areas that were affected. This strategy also entails cooperate approach by involving all relevant Government, Donor community, UN System, Private sector and NGOs agencies (both local and international). | 9311 | 10
40 | 5.0 REQUIRED INTERVENTIONS | 9636 | 10
41 | As reflected in the floods In-Depth Vulnerability and Needs Assessment report, the required interventions involve eight (8) sectors with activities ranging from those of short to medium and long term. The main sectors involved are those that the assessment established as having been severely affected by the floods. These are Health and Nutrition, Water and Sanitation, Infrastructure, Human settlement and Shelter, Education, Agriculture and Food Security. | 9665 | 10 |  | water, flood, flood
42 | These interventions are based on the fact that there is some level of response going on in each of these sectors. This level of response however, falls short of meeting the demands/needs in the floods affected districts. What is required therefore is the scaling up of the interventions so as to make them more effective and responsive to the needs of the floods affected districts. The required interventions are as summarised in the sector by activity in table 2 below: | 10131 | 10 |  | flood, flood
43 | 3 Table 2: Sector by Activity | 10610 | 11
44 | SECTOR 1. Education 2. Health | 10646 | 11
45 | ACTIVITY Carryout rehabilitation works on all school infrastructure damaged by floods, construction of school infrastructure (Classrooms, Teachers’ houses, VIP latrines) and at 76 identified Schools Procurement and Prepositioning of school in a box and recreational kits 1. Sub-activity: Disease Prevention and Treatment Support the procurement and distribution of essential drugs, vaccines and supplies Support the sustained delivery of essential health services such as immunization, child, maternity, HIV/AIDS, TB including through outreach where appropriate. Staff refresher training for prevention and control of flood related medical conditions (emergency triage, diarrhoeal diseases, plague etc Support integrated disease surveillance and reporting (IDSR) especially measles, polio and cholera surveillance. 2. Sub –activity: Health promotion Health education to communities (on good hygiene practices, disinfection of water and waste disposal, etc). 3. Sub-activity: Monitoring and Evaluation Monitoring, technical supervision and support visits 3. Nutrition | 10680 | 11 |  | disease, disease, disease, water, emergency, disease, disease, disease, disease, disease, disease, flood, flood, emergency, rain
46 | 4. Human Settlement and Shelter | 11766 | 11
47 | Support to mitigation of nutritional impact of floods on health (Supportive visits and continuous monitoring and evaluation). Training of community volunteers in Active Case Finding of malnourished in the flood affected areas. Training in management of severe malnutrition in the flood affected districts both for hospital and community management Procurement of supplementary and therapeutic feeds (HEPS, F 75 and F100, RUTF) for both malnourished U 5 children and adults Consultations with local leadership (traditional and district administration) on identification of safer lands Acquisition of such safe lands to resettle the communities vulnerable to flooding Conduct a survey among the concerned communities to determine their willingness to relocate to higher lands and educate them on possible livelihood sources Site preparation and development of new settlement | 11802 | 12 | Lunte | flood, flood, flood, flood, rain, rain
48 | 5. Infrastructure | 12692 | 12
49 | Repairs to Washed Away Bridges Construction of New Bridge Structure (Permanent) Repair Works to Damaged Culverts/Drifts 6. Social Protection 7. Water and Sanitation | 12712 | 12 |  | water
50 | 8. Agriculture and Food security Installation of New Culverts/Drifts Reinstatement of washed/eroded embankments and stone pitching Awareness raising Capacity building Psychosocial support 1. Sub activity: Water and Sanitation infrastructure (rehabilitation and Provision of safe water to affected communities (Household Chlorine, HTH Chlorine) Provision of water (boreholes) and sanitation (latrines) sinking/digging of new ones) Provision of water storage containers, soap and hand washing facilities. Improvement of water sources 2. Sub activity: Training Hygiene promoters and V-WASHE committees Water quality & quantity monitoring, proper usage of home chlorination and HTH, management of water and sanitation facilities and safe excreta disposal. Proper garbage handling and disposal Dry season crop production input support livestock disease vaccination Livestock dipping Procurement of 8,295.46 MTs of Relief food Transportation of 8,295.46 MTs of Relief food Distribution of 8,295.46 MTs of Relief food | 12885 | 12 |  | disease, water, water, water, water, water, water, water, disease, disease, War, rain |  | household, home
51 | 5 6.0 IMPLEMENTATION PLAN In order to ensure maximum participation of all stakeholders and at the same time ensure that Portfolio institutions and agencies take up their responsibilities as we scale-up the operation, the affected sectors in conjunction with relevant UN, NGO and Private sector agencies will be responsible for the implementation of their activities based on the sector needs as per attached sector specific annexes. Satellite Disaster Management Committees in conjunction with NGOs will be front line implementers while District Disaster Management Committees will be the overall district supervisors. | 13923 | 13
52 | 6.1 Current level of response As mentioned earlier, it is important to recognize that a lot has already been done by Government in collaboration with its co-operating partners in terms of response interventions. The implementation of this action plan should therefore be seen within the context of scaling up of the existing interventions based on the 2009 Rapid Assessment and not necessarily kick-starting of the recovery operation. | 14556 | 13 |  |  | 2009
53 | 6.2 Scaling Up In order to scale up the level of current response and make the operation more effective and responsive to the needs of the affected populations, it is important that the sector-based interventions are implemented as recommended (see Annexes 1 to 8 for more details). | 14999 | 13
54 | 7.0 ROLES AND RESPONSIBILITIES The major stakeholders such as the Ministries of Education, Health, Agriculture, Works and Supply, Department of Water Affairs, Local Government and Housing, Community Development, Finance and Donor community, the UN system, Private sector including NGOs both local and international will play an important role to | 15292 | 13 |  | water
55 | ensure that the planned programmes are timely and efficiently implemented in order for the programme to be effective and responsive enough to achieve the programme objectives. Each Ministry/Department will nominate a dedicated officer who will be part of the coordination core team to overseer the implementation of the recommended interventions. Satellite Disaster Management Committees in conjunction with NGOs will be the front line implementers of the interventions while District Disaster Management Committees (DDMC) will have the district overall supervisory responsibilities. | 15644 | 14
56 | 8.0 TIME FRAME The activities will be implemented within twelve (12) months beginning in July 2009. This period will cover the implementation of short to medium and some long-term interventions. | 16240 | 14 |  |  | July 2009
57 | 9.0 REPORTING ARRANGEMENTS All implementing agencies will generate progress reports and submit them to DMMU through the National Coordinator on monthly basis. DMMU will in turn consolidate the sector reports in one document and submit it to Government and other stakeholders for decision-making and information sharing. | 16440 | 14
58 | 10.0 COORDINATION | 16766 | 14
59 | The coordination of the implementation of the rehabilitation plan (short to medium and long term) will be spearheaded by DMMU supported by the Coordination Core Team with representation from Government, Donors, UN system, private sector and NGOs. | 16786 | 14
60 | 7 11.0 MONITORING AND EVALUATION | 17038 | 15
61 | Monitoring of the implementation of interventions will be based on the indicators as brought out in the monitoring and valuation indicators table (Refer to Table 3) and will be done at different levels namely: through reports, field trips involving a combined team of main stakeholders or individual institutions and organizations. Political leadership at national, provincial and local levels will be critical in ensuring that the objectives of this recovery action plan are achieved in line with its rationale. | 17077 | 15
62 | Effectiveness of the interventions will be evaluated in terms of outcomes and impact on the target population and districts. A final impact assessment will be conducted. The report will be presented to Government and shared with other stakeholders for important reflections on the response and recovery programme. | 17597 | 15
63 | 8 Table 3: Monitoring And Evaluation Indicator | 17916 | 16
64 | SECTOR RESPONSIBLE INSTITUTION ACTIVITIES OUTPUT INDICATORS OUTCOMES 1.Education MoE • Rehabilitate school infrastructure, teachers’ houses and construct VIP latrines • Procurement and Prepositioning of school in a box and recreational kits • No. of infrastructure teachers’ rehabilitated school and houses • No. of pit latrines constructed • No. of new schools constructed • No. of community schools upgraded 2. Health | 17969 | 16
65 | MoH • Disease prevention and treatment • Health promotion • Monitoring and evaluation 3. Nutrition MoH/NFNC | 18427 | 16 |  | disease, disease, disease
66 | • Support mitigation impact of nutritional of floods on health through growth monitoring • Training of community volunteers in Active Case Finding of malnourished in the flood affected areas • Training in management of severe malnutrition in the flood affected districts both for hospital and • No of school in a box and procured kits prepositioned • No. of ITNs distributed to children under five and pregnant women • No of cumulative acute diarrhoea estimated cases of • Estimated average rate diarrhoea acute of deaths • % of population with access to primary health care services • Estimated % of children under 5 covered by nutritional surveillance in the affected areas • Amount of therapeutic feeds procured. • Number trained in child feeding. of officers infant and • Number of nutrition education conducted • • • • • • • • Improved school Infrastructure Improved accommodation Improved sanitary facilities Improved school attendance teachers’ Improved child and women health Improved disease management Improved access to primary health care services Improved hygiene practices and waste disposal • Improved Nutrition status SECTOR RESPONSIBLE INSTITUTION ACTIVITIES OUTPUT INDICATORS OUTCOMES community management • Procurement of therapeutic feeds (HEPS, F 75 and F100) for both malnourished U 5 children and adults and provides nutrition education during distribution sessions. | 18543 | 17 | Lunte | disease, disease, disease, flood, flood, flood, rain, rain, rain
67 | • Identification of land for relocation in flood prone areas • No. of districts visited identify safer land flood prone to • People’s lives secured • No. of reduced Improved habitations houses collapsing 4.Human shelter and Settlement DMMU, DEPT.OF RESETTLEMENT UN, HABITAT, IOM • Consultation with local • No. of pieces of land • leadership • Community sensitization • Human settlement | 20030 | 17 |  | flood, flood
68 | identified of • No. consultative meetings held with local leadership RDA,ZNS.ZA • Repairs to washed away • No. of • Improved accessibility • No. of sensitization meetings held • No. of cartographic equipment procured • No. of persons resettled on safer land bridges/culverts/drifts reinstated/constructed bridges • Construction bridge (Permanent) of new structures • Repair works to damaged culverts/drifts Install new culverts/drifts • • Reinstate washed/eroded embankments and stone pitching 10 5. Infrastruct ure | 20448 | 17
69 | OUTPUT INDICATORS OUTCOMES • No of awareness campaigns children’s and the rights done on women’s communities in • No of prevention measures put in place Initiate and and promote community safety (prevention) family level • No of Psychosocial counseling sessions done • No. boreholes drilled • No. of hand pumps installed • No. of water committees trained • No. of sanitary facilities constructed • No of Hygiene promoters and committees V-WASHE members trained • No. of beneficiaries reached • Food security at household level • No. of animals vaccinated • protective environment children families created and for their • • • • • water Improved child and women health Improved supply Increased access to safe water Improved management Improved facilities sanitary disease • Enhanced agricultural production Improved animal health • | 21005 | 18 |  | agricultural, disease, water, water, water, disease, disease, War, rain, rain |  | household, family, families
70 | SECTOR 6.Social Protection RESPONSIBLE INSTITUTION MCDSS, MoH ACTIVITIES NGOs • Awareness raising • Capacity building • Psychosocial support 7.Water and Sanitation MEWD | 21907 | 18 |  | water, War
71 | • Water and sanitation • Training • Monitoring and evaluation MACO,MCDSS,DM MU 8.Agricultu re and Food Security | 22092 | 18 |  | water, rain
72 | • Provision of input (FSP) • Promote crop diversification • Animal disease control • Provision livestock of extension services and treated • Provision of livestock • Reduction in animal disease | 22212 | 18 |  | disease, disease, disease, disease, disease, disease
73 | husbandry practices | 22419 | 18
74 | • • Provision of relief food outbreaks • Total quantity of food aid • Nutrition status distributed improved | 22441 | 18
75 | 11 ANNEXES Annex 1: EDUCATION | 22557 | 19
76 | Problem statement and rationale The Education Sector was not spared from the effects of the floods that occurred during the 2008/09 rainfall season. Arising from that, learning was disrupted as School Infrastructure got submerged and damaged resulting in some schools being closed and others were operating at half capacity. | 22594 | 19 |  | flood, rain | 2008/09
77 | The Ministry of Education has assessed the impact of the floods and prioritized interventions as medium and long term to rehabilitate the damaged infrastructure and preposition school kits. | 22925 | 19 |  | flood
78 | Activities The activities to be implemented in the medium term and long term are mainly rehabilitation works on all school infrastructure damaged by floods, construction of school infrastructure (Classrooms, Teachers’ houses, VIP latrines) at 76 identified Schools, Procurement and Prepositioning of school in a box and recreational kits. | 23119 | 19 |  | flood
79 | Targets Carry out rehabilitation works at 76 schools in 20 districts in 6 provinces. | 23467 | 19
80 | Implementing Agency Ministry of Education will be the lead-implementing Agency and will be assisted by Cooperating Partners. | 23555 | 19
81 | Immediate Financial Requirements: ZMK 672,000,000.00 (US$134,400.00) | 23684 | 19
82 | 12 Table 4: Education Activity Budget | 23754 | 20
83 | Activity Resource required ZMK Resource available ZMK Net resource required ZMK Net resource required USD Site selection and planning 50,000,000.00 50,000,000.00 0.00 - Identify implementation partners Defining criteria for rehabilitation Procurement and Prepositioning of school in a box and recreational kits 1,000,000.00 15,000,000.00 1,000,000.00 15,000,000.00 0.00 0.00 - - 350,000,000,.00 | 23798 | 20
84 | 350,000,000.00 70,000.00 | 24223 | 20
85 | 1 2 3 4 5 Training on site planning and management 18,000,000.00 0 18,000,000.00 3,600.00 6 7 9 10 Assess the needs and design solution Provide necessary equipment and materials to construct temporally shelters Construct temporally classrooms and latrines Assess how the plan is working and make necessary changes to improve the situation Periodical monitoring to review situation on the ground to make corrections if need be 11 2,000,000.00 2,000,000.00 0.00 - 50,000,000.00 350,000,000.00 50,000,000.00 100,000,000.00 0.00 250,000,000.00 - 50,000.00 40,000,000.00 40,000,000.00 0.00 - 54,000,000.00 0.00 54,000,000.00 10,800.00 12 Evaluation of the implementation plan 41,000,000.00 41,000,000.00 0.00 - Carryout rehabilitation works on all school infrastructure damaged by floods | 24251 | 20 |  | flood, rain
86 | 13 | 25086 | 20
87 | 2,460,000,000.00 2,460,000,000.00 | 25091 | 20
88 | 0.00 | 25128 | 20
89 | - - | 25135 | 20
90 | TOTAL 7,081,000,000.00 3,299,000,000.00 672,000,000.00 134,400.00 | 25142 | 20
91 | 13 Cost Breakdown of Item 13 in the activity table above Districts Name of School Kapirimposhi Chambulumina Serenje Kamwala Basic | 25213 | 21 | Serenje
92 | Makopa Basic Ngauswe Nsabala Mambwe Chinyololo | 25354 | 21 | Mambwe
93 | Kakumbi Mfuwe St Lukes Secondary Kawambwa Muyembe | 25407 | 21 | Kawambwa
94 | Posa Activity Repairs One classroom Repairs to 2 classrooms and 1 house Repairs to 2 classrooms Repairs to 2 classrooms and 1 house Repairs to 3 classrooms, 4 houses 1 water point and 2 sanitation facility Repairs to 5 classrooms, 1 water point and 6 sanitation facilities Repairs to 2 classrooms Repairs to 6 classrooms, 2 water point and 6 sanitation facility Repairs to 2 classrooms Repairs to 1 classroom and 1 water point Resource required ZMK Resource available ZMK Net resource required ZMK | 25464 | 21 |  | water, water, water, water
95 | 9,000,000.00 9,000,000.00 - 24,000,000.00 24,000,000.00 - | 26004 | 21
96 | 18,000,000.00 18,000,000.00 - | 26069 | 21
97 | 24,000,000.00 | 26103 | 21
98 | 24,000,000.00 | 26119 | 21
99 | - - 57,000,000.00 57,000,000.00 - | 26135 | 21
100 | 65,000,000.00 65,000,000.00 - | 26175 | 21
101 | 18,000,000.00 18,000,000.00 - | 26209 | 21
102 | 76,000,000.00 76,000,000.00 - 18,000,000.00 18,000,000.00 - | 26243 | 21
103 | 11,000,000.00 11,000,000.00 - | 26310 | 21
104 | 14 | 26344 | 22
105 | Districts Name of School | 26352 | 22
106 | Salangi Mpika Chibaye | 26381 | 22 | Mpika
107 | Chikakala Chipundu Lifunda Lulimala Munelu Mupamadzi Mpolokoso Chewe | 26407 | 22
108 | Chinika Chiwala Fibwe Activity Repairs to 2 classrooms, 4 houses and 4 sanitation facility Repairs to 3 classrooms, 1 water point and 3 sanitation facilities Repairs to 3 classrooms, 1 house and 3 sanitation facilities Repairs to 2 classrooms and 1 house Repairs to 3 classrooms Repairs to 3 classrooms, and 3 sanitation facilities Repairs to 3 classrooms, and 5 sanitation facilities Repairs to 2 classrooms and 1 house Repairs to 2 classrooms Repairs to 2 classrooms Repairs to 2 classrooms and 2 sanitation facilities Repairs to 2 classrooms and 1 sanitation facility Resource required ZMK Resource available ZMK Net resource required ZMK 54,000,000.00 54,000,000.00 - | 26485 | 22 |  | water
109 | 38,000,000.00 38,000,000.00 - | 27210 | 22
110 | 42,000,000.00 42,000,000.00 - | 27244 | 22
111 | 24,000,000.00 24,000,000.00 - | 27278 | 22
112 | 27,000,000.00 27,000,000.00 - | 27312 | 22
113 | 36,000,000.00 36,000,000.00 - | 27346 | 22
114 | 42,000,000.00 42,000,000.00 - | 27380 | 22
115 | 24,000,000.00 24,000,000.00 - 18,000,000.00 18,000,000.00 - | 27414 | 22
116 | 18,000,000.00 18,000,000.00 - | 27481 | 22
117 | 24,000,000.00 24,000,000.00 - | 27515 | 22
118 | 21,000,000.00 21,000,000.00 - | 27549 | 22
119 | 15 | 27583 | 23
120 | Districts Name of School | 27591 | 23
121 | Kalabwe Kambobe Kanyimba Ley Mungwi Kayambi | 27620 | 23 | Nyimba, Mungwi
122 | Mpoopo Mumba Ndasa Shimps St Francis High Chavuma Chambi | 27671 | 23 | Chavuma
123 | Chivumbo Kakoma Activity Repairs to 3 classrooms, 1 water point and 3 sanitation facilities Repairs to 3 classrooms, 1 house and 3 sanitation facilities Repairs to 2 classrooms and 1 house Repairs to 3 classrooms Repairs to 3 classrooms Repairs to 3 classrooms, and 3 sanitation facilities Repairs to 3 classrooms, and 5 sanitation facilities Repairs to 2 classrooms and 1 house Repairs to 2 classrooms Repairs to 2 classrooms Repairs to 2 classrooms and 1 house Repairs to 3 classrooms Repairs to 3 classrooms, and 3 sanitation facilities Resource required ZMK Resource available ZMK Net resource required ZMK 38,000,000.00 38,000,000.00 - | 27736 | 23 |  | water
124 | 42,000,000.00 42,000,000.00 - | 28429 | 23
125 | 24,000,000.00 24,000,000.00 - 27,000,000.00 27,000,000.00 - | 28463 | 23
126 | 27,000,000.00 27,000,000.00 - | 28530 | 23
127 | 36,000,000.00 36,000,000.00 - | 28564 | 23
128 | 42,000,000.00 42,000,000.00 - | 28598 | 23
129 | 24,000,000.00 24,000,000.00 - | 28632 | 23
130 | 18,000,000.00 18,000,000.00 - 18,000,000.00 18,000,000.00 - | 28666 | 23
131 | 24,000,000.00 24,000,000.00 - | 28733 | 23
132 | 27,000,000.00 27,000,000.00 - | 28767 | 23
133 | 36,000,000.00 36,000,000.00 - | 28801 | 23
134 | 16 | 28835 | 24
135 | Districts Name of School | 28843 | 24
136 | Ligundu Kabompo Dyambombola | 28872 | 24 | Kabompo
137 | Kabulamena Kashinskazhi Mayau Kasempa Ingwe | 28903 | 24 | Kasempa
138 | Kakolokolo Kalombe Kamakechi Kamakuku Njenga Mufumbwe Kashima East | 28953 | 24 | Mufumbwe
139 | Matushi Activity Repairs to 3 classrooms, 1 water point and 3 sanitation facilities Repairs to 3 classrooms, 1 house and 3 sanitation facilities Repairs to 2 classrooms and 1 house Repairs to 3 classrooms Repairs to 3 classrooms Repairs to 3 classrooms, and 3 sanitation facilities Repairs to 3 classrooms, and 3 sanitation facilities Repairs to 3 classrooms, and 5 sanitation facilities Repairs to 2 classrooms and 1 house Repairs to 2 classrooms Repairs to 2 classrooms Repairs to 2 classrooms and 2 sanitation facilities Repairs to 2 classrooms and 1 Resource required ZMK Resource available ZMK Net resource required ZMK 38,000,000.00 38,000,000.00 - | 29028 | 24 |  | water
140 | 42,000,000.00 42,000,000.00 - | 29734 | 24
141 | 24,000,000.00 24,000,000.00 - 27,000,000.00 27,000,000.00 - | 29768 | 24
142 | 27,000,000.00 27,000,000.00 - | 29835 | 24
143 | 36,000,000.00 36,000,000.00 - | 29869 | 24
144 | 36,000,000.00 36,000,000.00 - | 29903 | 24
145 | 42,000,000.00 42,000,000.00 - | 29937 | 24
146 | 24,000,000.00 24,000,000.00 - | 29971 | 24
147 | 18,000,000.00 18,000,000.00 - 18,000,000.00 18,000,000.00 - | 30005 | 24
148 | 24,000,000.00 24,000,000.00 - | 30072 | 24
149 | 21,000,000.00 21,000,000.00 - | 30106 | 24
150 | 17 | 30140 | 25
151 | Districts Name of School | 30148 | 25
152 | Shukwe Mwinilunga Jimbe | 30177 | 25 | Lunga, Mwinilunga
153 | Zambezi | 30205 | 25 | Zambezi
154 | Kakoma Luwvi Matonchi Mukangala Mumpulumbu Ntambu Lweji Malola Kanchale Activity sanitation facility Repairs to 3 classrooms, 1 water point and 3 sanitation facilities Repairs to 3 classrooms, 1 water point and 3 sanitation facilities Repairs to 3 classrooms, 1 house and 3 sanitation facilities Repairs to 3 classrooms Repairs to 3 classrooms Repairs to 3 classrooms, and 3 sanitation facilities Repairs to 3 classrooms, and 5 sanitation facilities Repairs to 2 classrooms and 1 house 1 water point and 6 sanitation facilities Repairs to 2 classrooms Repairs to 2 classrooms Repairs to 2 classrooms and 1 house Resource required ZMK Resource available ZMK Net resource required ZMK 38,000,000.00 38,000,000.00 - | 30215 | 25 |  | water, water, water
155 | 38,000,000.00 38,000,000.00 - | 30986 | 25
156 | 42,000,000.00 42,000,000.00 - 27,000,000.00 27,000,000.00 - | 31020 | 25
157 | 27,000,000.00 27,000,000.00 - | 31087 | 25
158 | 36,000,000.00 36,000,000.00 - | 31121 | 25
159 | 42,000,000.00 42,000,000.00 - | 31155 | 25
160 | 24,000,000.00 24,000,000.00 - 18,000,000.00 18,000,000.00 - | 31189 | 25
161 | 18,000,000.00 18,000,000.00 - | 31256 | 25
162 | 24,000,000.00 24,000,000.00 - | 31290 | 25
163 | 18 | 31324 | 26
164 | Districts Name of School | 31332 | 26
165 | Mangongi Kaoma Kanchale | 31361 | 26 | Kaoma
166 | Mangongi Lukulu Lutembwe | 31389 | 26 | Lukulu
167 | Lyande Mataba Nalonde Senanga Chikwiba | 31418 | 26 | Senanga
168 | Ikeleenge Luwi Mande Senanga Activity Repairs to 3 classrooms Repairs to 2 classrooms and 1 house Repairs to 3 classrooms Repairs to 3 classrooms, and 3 sanitation facilities Repairs to 3 classrooms, 1 water point and 3 sanitation facilities Repairs to 3 classrooms, 1 house and 3 sanitation facilities Repairs to 5 classrooms, 1 water point and 6 sanitation facilities Repairs to 2 classrooms Repairs to 6 classrooms, 2 water point and 6 sanitation facility Repairs to 2 classrooms Repairs to 1 classroom and 1 water point Repairs to 2 classrooms, 4 houses and 4 Resource required ZMK Resource available ZMK Net resource required ZMK | 31463 | 26 | Senanga | water, water, water, water
169 | 27,000,000.00 27,000,000.00 - 24,000,000.00 24,000,000.00 - | 32149 | 26
170 | 27,000,000.00 27,000,000.00 - | 32216 | 26
171 | 36,000,000.00 36,000,000.00 - | 32250 | 26
172 | 38,000,000.00 38,000,000.00 - | 32284 | 26
173 | 42,000,000.00 42,000,000.00 - | 32318 | 26
174 | 65,000,000.00 65,000,000.00 - 18,000,000.00 18,000,000.00 - | 32352 | 26
175 | 76,000,000.00 76,000,000.00 - | 32419 | 26
176 | 18,000,000.00 18,000,000.00 - | 32453 | 26
177 | 11,000,000.00 11,000,000.00 - | 32487 | 26
178 | 54,000,000.00 54,000,000.00 - | 32521 | 26
179 | 19 | 32555 | 27
180 | Districts Name of School Shangombo Buewa | 32563 | 27
181 | Lilonda Nangweshi Sesheke Limpumpu | 32610 | 27 | Sesheke
182 | Activity sanitation facility Repairs to 3 classrooms, 1 water point and 3 sanitation facilities Repairs to 3 classrooms, 1 water point and 3 sanitation facilities Repairs to 2 classrooms and 1 house 6 sanitation facilities Repairs to 3 classrooms Repairs to 3 classrooms Repairs to 3 classrooms, and 3 sanitation facilities GRAND TOTAL | 32650 | 27 |  | water, water
183 | Resource required ZMK Resource available ZMK Net resource required ZMK 38,000,000.00 38,000,000.00 - | 33009 | 27
184 | 38,000,000.00 38,000,000.00 - | 33123 | 27
185 | 76,000,000.00 76,000,000.00 - | 33157 | 27
186 | 27,000,000.00 27,000,000.00 - 27,000,000.00 27,000,000.00 - | 33191 | 27
187 | 36,000,000.00 2,460,000,000.00 36,000,000.00 2,460,000,000.00 - - 20 Table 5: Education Implementing Schedule | 33258 | 28
188 | ACTIVITIES MEDIUM TERM Identify damaged school sites and develop bills of Quantities, schedule of materials Identify small contractors and enter into labour contract for the rehabilitation of classrooms, teachers' houses and construction of VIP latrines at the schools affected by the floods Rehabilitation of School Infrastructure and Teachers' houses and construction of VIP Latrines at schools affected by the floods. Procurement and Prepositioning of school in a box and recreational kits Periodical monitoring to review situation on the ground | 33380 | 28 |  | flood, flood
189 | Aug | 33944 | 28
190 | Sep Year 2009 Nov Oct Dec Year 2010 | 33950 | 28 |  |  | 2010
191 | Feb | 33993 | 28
192 | Mar Apr May Jun | 33999 | 28
193 | Jan | 34020 | 28
194 | Aug | 34026 | 28
195 | Sep | 34032 | 28
196 | 21 | 34038 | 29
197 | Annex 2: HEALTH | 34046 | 29
198 | PROBLEM STATEMENT Reference is made to the 2009 heavy rains that caused numerous health problems in the assessed 20 districts in the country. The health sector experienced challenges as follows; • Disruption of health services such as inaccessible health facilities and the resulting surge in demand at other service delivery points is likely to result in shortages of essential drugs /supplies and overburdened health staff. • Pooling of water leading to an increase in the mosquito breeding sites and a possible increase in the cases of malaria especially after the flood water recedes. • Cross-contamination of drinking water sources and faecal disposal facilities coupled with the difficulties faced to access alternative safe water sources may result in epidemics of diarrhoeal diseases such as cholera and dysentery. • Overcrowding of displaced people in their places of resettlement may lead to respiratory tract infection and outbreaks of immunizable diseases especially measles. • The displaced people especially children and pregnant women are likely to miss their immunization schedules and their antenatal services leaving them vulnerable to contracting preventable diseases. | 34064 | 29 |  | disease, disease, disease, water, water, water, water, shortage, disease, disease, disease, disease, disease, disease, flood, disruption, rain | 2009
199 | ACTIVITIES • Disease prevention and treatment. • Health education. • Monitoring and evaluation. | 35273 | 29 |  | disease, disease, disease
200 | Immediate Financial Requirements: ZMK 913,276,775(US$182,655.36) | 35374 | 29
201 | Table 6: Health Activity Schedule | 35441 | 30
202 | ACTIVITY RESOURCE RESOURCES GAP TIME FRAME 2009 COMMENT REQUIRED AVAILABLE Jul Aug Sep Oct Nov Dec 1. Sub-activity: health (Disease Prevention and Treatment Support the 109,386,400 0 109,386,400 | 35480 | 30 |  | disease, disease, disease | 2009
203 | procurement and distribution of essential drugs, vaccines and supplies Support the 85,000,000 0 85,000,000 | 35690 | 30
204 | sustained delivery of essential health services such as immunization, child, maternity, HIV/AIDS, TB including through outreach where appropriate. | 35810 | 30
205 | Staff refresher 160,000,000 0 160,000,000 | 35972 | 31
206 | training for prevention and control of flood related medical conditions (emergency triage, diarrhoeal diseases, plague etc Support 121,290,375 0 121,290,375 | 36022 | 31 |  | disease, emergency, disease, disease, flood, emergency, rain
207 | integrated disease surveillance and reporting (IDSR) especially measles, polio and cholera surveillance. 2. Sub –activity: health promotion Health education 398,000,000 0 398,000,000 | 36195 | 31 |  | disease, disease, disease
208 | to communities | 36393 | 31
209 | 24 (on good hygiene practices, disinfection of water and waste disposal, etc). 3. Sub-activity: Monitoring and Evaluation Monitoring, 39,600,000 0 39,600,000 | 36411 | 32 |  | water
210 | technical supervision and support visits GRAND TOTAL | 36585 | 32
211 | 913,276,775 | 36644 | 32
212 | 25 Table 7: Essential Drugs and Supplies LIST OF ESSENTIAL DRUGS AND SUPPLIES NO. ITEM QUANTITY UNIT TOTAL 1 2 3 | 36658 | 33
213 | Insecticide Treated Nets ORS Antimalarials 1,000 5,000 satchets PRICE(K) COST(K) 30,000 30,000,000 2,000 10,000,000 Arthemeter- lumefantrine 12’s 200pac 178,000 35,640,000 (coartem)[20/120] 18’s & 12’s 4 Sulfadoxine- pyrimethamine tabs 20pac of 119,800 2,396,400 1000 tab | 36784 | 33
214 | Quinine 300mg tab 300pac of 1920 576,000 100tab Quinine injection (300mg/ml) 100boxes 7,500 750,000 2ml ampoules 5 Antibacterials | 37080 | 33
215 | Metronidazole(250mg) 50pac 48,180 2,409,000 Cotrimoxazole 100pac 23,500 2,350,000 Ciprofloxacin(250mg) 200pac 1,620 324,000 6 Intravenous fluids | 37225 | 33
216 | Ringers lactate 500mls W/gset 40 boxes 110,000 4,400,000 5% dextrose w/gset 20 boxes 112,000 2,240,000 50% dextrose (10ml bottles 160 boxes 18,000 2,880,000 Normal saline 500mls W/gset 15 boxes 117,000 1,755,000 7 Canulae | 37385 | 33
217 | 14G 16G 18G 8 Syringes | 37626 | 33
218 | 500 500 1,000 1,200 1,200 1,200 600,000 600,000 600,000 | 37655 | 34
219 | 2ml 5ml 10ml 25x 100 50x100 5x100 120 180 252 300,000 900,000 126,000 Cotton wool 500g x 400 11,500 4,600,000 Methylated spirit 2.5litres 2.5litresx 15,000 4,500,000 300 Plaster/strapping 120x 10cm 12,000 1,440,000 Total | 37724 | 34
220 | 109,386,400 27 Annex 3: NUTRITION Problem Statement Floods are likely to cause numerous health and nutritional problems in the country. An anticipated increase in levels of food and nutrition insecurity and diseases related to overcrowding is inevitable. The broad nutrition sector challenges include the following: | 37970 | 35 |  | disease, disease, disease, flood
221 | • Disruption of preventive health and nutrition services such as inaccessible health facilities and inadequate Growth Monitoring and promotion service points and the resulting surge in demand at other service delivery points is likely to result in shortages of essential medicines and nutrition supplies and over-stretched health staff. | 38298 | 35 |  | shortage, disruption
222 | • Resultant household food and nutrition insecurity will lead to malnutrition and increased susceptibility to infectious and immunizable diseases such as measles. | 38641 | 35 |  | disease, disease, disease |  | household
223 | Activities The mitigation measures for Nutrition fall under the broad categories as shown in table1 below. | 38812 | 35
224 | Financial Requirements: ZMK3,323,765,850.60(US$664,753.17) | 38923 | 35
225 | 28 Table 8: Nutrition Activity Schedule | 38984 | 36
226 | NUTRITION SECTOR FLOOD DISASTER RESPONSE ACTIVIVTY Resource required Resource Avail Gap Timeframe (2010) Q1 Q2 Q3 Q4 Comment Sub-activity: Nutrition Support to mitigation of nutritional impact of floods on health (Supportive visits and continuous monitoring and evaluation). Training of community volunteers in Active Case Finding of malnourished in the flood affected areas. Training in management of severe malnutrition in the flood affected districts both for hospital and community management Procurement of supplementary and therapeutic feeds (HEPS, F 75 and F100, RUTF) for both malnourished U 5 children and adults GRAND TOTALS 500,000,000.00 0 500,000,000.00 250, 000, 050.00 300, 000, 050.00 2,823,765,750.60 3,873,765,850.60 | 39030 | 36 | Lunte | flood, flood, flood, flood, rain, rain
227 | 0 0 | 39799 | 36
228 | 250,000,050.00 300,000,050.00 2,823,765,750.60 3,873,765,850.60 | 39806 | 36
229 | Assistance with transport will be required | 39875 | 36
230 | Currently what is available in the country is for routine therapeutic services (therapeutic feeding for non-complicated cases | 39921 | 36
231 | Target This plan targets the districts moderately or severely affected by floods. The classification is based on reports sent to DMMU, field reports, key informant interviews and the in-depth vulnerability assessment. | 40052 | 36 |  | flood
232 | Implementing Agency | 40274 | 36
233 | The National Food and Nutrition Commission, the Ministry of Health and its various Cooperating partners operating in the field of nutrition sectors will implement this plan. | 40296 | 36
234 | Annex 4: HUMAN SETTLEMENT AND SHELTER | 40473 | 37
235 | Problem Statement | 40516 | 37
236 | During the 2008/09 rainfall season, a number of districts experienced floods which led to the displacement of a number of households. | 40536 | 37 |  | flood, rain | 2008/09 | household, households
237 | The vulnerability of the affected households was enhanced by the fact that households were located in the flood prone areas coupled with the weak housing structures due to weak building materials used which are mainly pole, mud and grass. | 40673 | 37 |  | flood |  | household, household, households, households
238 | Although the impact of floods on human settlements was low in terms of the number of households affected, there is need to reduce such vulnerability and the impact of floods by realigning the settlement pattern of low lying areas prone to flooding by relocating them to higher and safer lands. | 40917 | 37 |  | flood, flood, flood |  | household, households
239 | Furthermore, there is need to sensitize the vulnerable communities on the dangers of settling in flood water channels and the benefits of building better structures on higher and safer lands as a permanent solution. | 41217 | 37 |  | water, flood
240 | Activities 1. consultations with local leadership (traditional and district administration) on identification of safer lands 2. acquisition of such safe lands to resettle the communities vulnerable to flooding | 41438 | 37 |  | flood
241 | 30 3. conduct a survey among the concerned communities to determine their willingness to relocate to higher lands and educate them on possible livelihood sources 4. site preparation of the new settlement a. boundary delineation b. plot demarcation c. road clearing d. borehole drilling e. plot allocation f. resettling of the new settlers The action plan will be implemented in two phases. The affected districts by order of severity are as follows: - | 41654 | 38
242 | Phase I In phase 1, districts along the Zambezi River catchments are targeted. These are i. Shangombo’ ii. Senanga iii. Kalabo | 42123 | 38 | Zambezi, Kalabo, Senanga
243 | Phase II In this phase, the following districts are targeted; i. Mambwe ii. Kaoma iii. Lukulu | 42257 | 38 | Mambwe, Kaoma, Lukulu
244 | 31 Implementation Agency a. The Department of Resettlement in conjunction with the Department of Physical Planning and Housing, UN-HABITAT, IOM, District Councils, Red Cross etc. b. DMMU will coordinate the implementation | 42357 | 39
245 | Financial Requirements: An estimated budget total of ZMKK662, 920,000(US$136,584.00) will be required to undertake the above alluded to activities in both phases one and two. | 42591 | 39
246 | 32 Table 9: Human Settlement and Shelter Activity matrix and Budget | 42770 | 40
247 | Activity Matrix | 42844 | 40
248 | Activity Resources Required Resources Available Resource Gap A Identification of Safer Lands for Resettling the Displaced Phase I | 42862 | 40
249 | 1 2 3 4 5 6 7 | 42999 | 40
250 | B | 43021 | 40
251 | C | 43025 | 40
252 | Hand Tools Protective Wear Survey and Mapping Printing of Maps Advertisements and Publicity Allowances Petrol Oil and Lubricants Toal For Land Identification | 43029 | 40
253 | Identification of Safer Lands for Resettling the Displaced Phase II Allowances Petrol Oil and Lubricants Community Sensitization on Relocation | 43196 | 40
254 | Facilitation of Resettlement of Displaced Persons in phases I and II Road Infrastructure Development in Phases I and II Road Pegging and Clearing Road Formation Monitoring and Evaluation Total For Road Infrastructure Development | 43344 | 40
255 | D Water Supply Development in Phases I and II Borehole Tendering 8 X Boreholes Sitting and Drilling Total for Water Supply Development | 43581 | 40 |  | water, water
256 | Grand Total | 43722 | 40
257 | 4,800,000 2,300,000 5,400,000 9,500,000 3,000,000 51,350,000 16,000,000 92,350,000 30,000,000 15,000,000 30,000,000 75,000,000 90,000,000 340,000,000 30,000,000 460,000,000 15,000,000 200,000,000 215,000,000 | 43736 | 40
258 | 31,000,000 20,000,000 0 51,000,000 32,107,500 32,107,500 10,200,327 74,415,327 4,000,000 50,014,673 54,014,673 4,800,000 2,300,000 5,400,000 9,500,000 3,000,000 51,350,000 16,000,000 92,350,000 -1,000,000 -5,000,000 30,000,000 24,000,000 57,892,500 307,892,500 19,799,673 385,584,673 11,000,000 149,985,327 160,985,327 842,350,000 179,430,000 662,920,000 33 Table 10: Human Settlement and Shelter Schedule | 43964 | 41
259 | ACTIVITY MATRIX | 44409 | 41
260 | t c i r t s D i | 44427 | 41
261 | l | 44444 | 41
262 | o b a a K d n a o b m o g n a h S a g n a n e S , Phase I | 44447 | 41
263 | Phase II | 44507 | 41
264 | a m o a K d n a u u k u L | 44518 | 41
265 | l | 44545 | 41
266 | , e w b m a M | 44548 | 41
267 | Month Identification of Safer Lands Community Sensitization Procurement of Hand Tools Surveying Area Boundary Layout Planning Plot Demarcation Road Pegging and Clearing Road Formation Borehole Sitting Borehole Drilling July Aug Sep Oct Nov Dec Apr May Jun Jul Aug Sep | 44563 | 41
268 | 34 | 44858 | 42
269 | Annex: 5. INFRASTRUCTURE Problem Situation: Road infrastructure, such as embankments, bridges and culverts, were damaged in some parts of the country due to heavy rains. The hardest hit areas are the Eastern, Northern, Western, Lusaka and Copperbelt provinces of the country. This has impacted negatively on the social service delivery and economic development. Rationale | 44866 | 42 | Lusaka | rain
270 | To develop road infrastructure sector specific inputs to the national response strategy document. Therefore, there is need to carryout urgent reinstatements to the affected road infrastructure in order to restore accessibility to areas affected and ensure that: | 45247 | 42
271 | • Access to health centers, schools, market places and agricultural areas is restored; • The much-needed relief supplies are delivered to the affected communities. | 45514 | 42 |  | agricultural
272 | Activities The proposed intervention measures are outlined below: • Repair and installation of washed away culverts; • Reinstatement of washed/eroded embankments and stone pitching the embankments; • Replacement of rotten timber bridges; • Reinforcing the existing bridge decks; • Reinstatement of washed away bridges with permanent structures; • Provision of vented drifts to allow for overtopping; and • Heavy dredging works using specialized machinery for the clearing and construction of channels. | 45683 | 42
273 | Target The target is to reinstate the following 327 road and drainage structures in the 66 districts which experienced severe floods: • Thirty two (32) Bridges; • Two hundred and Seventy Three (273) Culverts; • Seventeen (17) Embankment structures; and • Five (05) road sections that have experienced severe erosion. | 46197 | 42 |  | flood, rain
274 | 35 | 46522 | 43
275 | Implementing Agency a. Road Development Agency b. Zambia National Service c. Zambia Army d. Rural Roads Unit under Buildings Department. | 46530 | 43
276 | Financial Requirements: ZMK62,644,546,746(US$12,528,909.35) | 46673 | 43
277 | 36 | 46735 | 44
278 | Table 11: Summary of Number Of Structures Assessed | 46743 | 44
279 | No. Name of Province Bridges Culverts/Drifts Road Sections Embankments No. of Structures Assessed Total No. of Structures Assessed Estimate Cost Reinstatement (ZMK) 3 5 6 2 9 1 4 7 Central Copperbelt Eastern Luapula Lusaka North-Western Northern Southern 8 Western 1 5 12 0 0 6 4 1 3 12 42 95 12 16 37 36 15 8 Total 32 273 0 0 0 0 0 3 0 2 0 5 0 2 0 0 0 5 2 1 7 13 49 2,670,000,000.00 | 46796 | 44 | Lusaka
280 | 5,032,000,000.00 | 47257 | 44
281 | 107 18,963,000,000.00 12 16 51 42 19 18 | 47276 | 44
282 | 2,029,067,546.32 | 47325 | 44
283 | 6,370,479,200.00 4,581,000,000.00 | 47344 | 44
284 | 10,750,000,000.00 | 47381 | 44
285 | 4,293,000,000.00 | 47401 | 44
286 | 7,956,000,000.00 | 47420 | 44
287 | 17 327 62,644,546,746.32 | 47439 | 44
288 | Table 12: Infrastructure Activity Costs per Province | 47468 | 45
289 | Bridges Culverts/Drifts Embankment No. Province Repairs to Washed Away Bridges (ZMK) Construction of New Bridge Repair Works Structures to Damaged (Permanent) Culverts/Drifts Installation of New Pipe Culverts/Drifts (ZMK) Reinstatement of Eroded Embankments & Stone Pitching (ZMK) Overall Cost (ZMK) ZMK | 47526 | 45
290 | 200,000,000 | 47856 | 45
291 | - 1,360,000,000 | 47870 | 45
292 | 3,350,000,000 - - 4,902,979,200 | 47889 | 45
293 | - | 47926 | 45
294 | 650,000,000 1,820,000,000 | 47930 | 45
295 | - | 47959 | 45
296 | 2,670,000,000 | 47963 | 45
297 | 960,000,000 2,320,000,000 392,000,000 5,032,000,000 | 47979 | 45
298 | - | 48036 | 45
299 | 2,029,067,546 | 48040 | 45
300 | - - | 48056 | 45
301 | 982,500,000 | 48063 | 45
302 | - | 48077 | 45
303 | 2,029,067,546 | 48081 | 45
304 | 485,000,000 6,370,479,200 | 48097 | 45
305 | 2,046,000,000 1,000,000,000 9,877,000,000 2,690,000,000 18,963,000,000 7 Central 2 Copperbelt 5 Eastern 6 Luapula 8 Lusaka 1 North- Western 4 Northern 3 Southern 9 Western 998,000,000 70,000,000 140,000,000 1,286,000,000 2,087,000,000 4,581,000,000 | 48126 | 45 | Lusaka
306 | 800,000,000 2,500,000,000 1,300,000,000 | 48400 | 45
307 | 1,140,000,000 | 48444 | 45
308 | - - 5,800,000,000 | 48460 | 45
309 | - - - 1,395,000,000 835,000,000 | 48482 | 45
310 | 1,650,000,000 10,750,000,000 | 48520 | 45
311 | 1,598,000,000 4,293,000,000 | 48552 | 45
312 | 5,981,000,000 7,956,000,000 Cost Per Activity | 48583 | 45
313 | 6,484,000,000 | 48634 | 45
314 | 12,182,979,200 | 48650 | 45
315 | 2,750,000,000 | 48667 | 45
316 | 26,344,567,546 | 48683 | 45
317 | 14,883,000,000 62,644,546,746 | 48700 | 45
318 | Table 13: Infrastructure Activity Matrix | 48733 | 46
319 | Type of Structure Activity Resources Required Resources Available GAP (ZMK) (ZMK) (ZMK) Bridges Culverts Embankments Repairs to Washed Away Bridges Construction of New Bridge Structures (Permanent) Repair Works to Damaged Culverts/Drifts Installation of New Culverts/Drifts Reinstatement of washed/eroded embankments and stone pitching GRAND TOTAL | 48779 | 46
320 | 6,484,000,000 | 49151 | 46
321 | 12,182,979,200 | 49167 | 46
322 | 2,750,000,000 26,344,567,546 | 49184 | 46
323 | 6,484,000,000 | 49216 | 46
324 | 12,182,979,200 | 49232 | 46
325 | - - - 26,344,567,546 2,750,000,000 | 49249 | 46
326 | 14,883,000,000 | 49290 | 46
327 | 14,883,000,000 | 49307 | 46
328 | 62,644,546,746 | 49324 | 46
329 | - 62,644,546,746 | 49341 | 46
330 | Total Financial Requirement: ZMK 62,644,546,746 | 49361 | 46
331 | NOTE | 49412 | 46
332 | The Annual Work Plan 2009 for the RDA allowed for an amount of 5 Billion Kwacha for emergencies which has since been used and exhausted for other major emergencies on the Lusitu Bridge in Lusaka province and reinstatement of culverts on the Chipata Lundazi road in Eastern province | 49419 | 46 | Chipata, Lundazi, Lusaka |  | 2009
333 | 39 | 49705 | 47
334 | The projects were listed in order of priority from all the districts. The first three were taken as priority 1,2, and 3, if the district had more than three projects the process was repeated for the remaining ones until all projects were classified. | 49713 | 47
335 | Table 14: Infrastructure Priority Cost List Per Province Bridges Culverts/Drifts | 49967 | 47
336 | No. Province Priority 1 Priority 2 Priority 3 Overall Cost (ZMK) 7 2 5 6 8 1 4 3 Central Copperbelt Eastern Luapula Lusaka North- Western Northern Southern 9 Western Cost Per Activity | 50052 | 47 | Lusaka
337 | 1,540,000,000 3,150,000,000 7,987,000,000 880,945,722 2,209,437,600 1,398,000,000 4,885,000,000 2,044,000,000 5,146,000,000 29,240,383,322 | 50261 | 47
338 | 650,000,000 967,000,000 5,510,000,000 791,394,716 2,623,172,000 1,851,000,000 3,090,000,000 1,626,000,000 2,310,000,000 19,418,566,716 40 | 50411 | 47
339 | 480,000,000 915,000,000 5,466,000,000 356,727,109 1,537,869,600 1,332,000,000 2,775,000,000 623,000,000 500,000,000 13,985,596,709 | 50561 | 47
340 | 2,670,000,000 5,032,000,000 18,963,000,000 2,029,067,546 6,370,479,200 4,581,000,000 10,750,000,000 4,293,000,000 7,956,000,000 62,644,546,746 | 50703 | 48
341 | Table 15 : Infrastructure Implementation Schedule | 50860 | 48
342 | Activity No. Activity 2009 2010 Aug Sept Oct Nov Dec Jan Feb Mar Apr May June July Aug Sep Oct Nov 1 2 3 4 5 Repairs to Washed Away Bridges Construction of New Bridge Structures (Permanent) Repair Works to Damaged Culverts/Drifts Installation of New Culverts/Drifts Reinstatement of washed/eroded embankments and stone pitching | 50912 | 48
343 | 41 Annex 6: SOCIAL PROTECTION | 51266 | 49
344 | Problem statement and rationale There assessment established that some children and women experienced some form of violence during the floods in the districts visited. Some communities had no prevention measures to violence while others did not have reporting mechanisms in place. | 51302 | 49 |  | flood
345 | Children and women protection should ideally seek to prevent and put an end to violence, exploitation and abuse against children, women and other vulnerable groups during an emergency. This should be done by strengthening the ability of individuals and families to protect themselves from future threats thereby laying the foundation for lasting security and stability. Individuals and families will only be able protect themselves if all stakeholders and child protection workers endeavor to create a protective environment which will warrant protection in emergency situations. | 51589 | 49 |  | emergency, emergency, emergency, emergency, threat, War |  | families, families
346 | Activities The mitigation measures for the Protection sector will include the following: | 52178 | 49
347 | • Initiate and promote family and community level safety (prevention) • Capacity building and awareness raising on children’s and women’s rights • Psychosocial counseling All activities will be centered on creating a protective environment for children and their families. | 52270 | 49 |  | War |  | family, families
348 | Implementing Agencies • Ministry of Community Development and Social Services • Ministry of Local Government and Housing • Ministry of Health | 52549 | 49
349 | • Cooperating Partners • Private Sector • Non Governmental Organizations | 52696 | 50
350 | Financial Requirements: 6,725,000,000(US$1,345,000.00) | 52776 | 50
351 | 43 Table 16: Social Protection Activity Budget | 52833 | 51
352 | Awareness Raising | 52886 | 51 |  | War
353 | Affected Population Cost Capacity Building Psychosocial | 52907 | 51
354 | Cost Cost Total Cost 44567 30618 10775 30237 37622 28506 35566 6919 15593 14425 22661 27456 13719 28846 40614 14360 35956 24106 18341 18469 220,000,000 150,000,000 50,000,000 150,000,000 185,000,000 140,000,000 175,000,000 35,000,000 75,000,000 70,000,000 110,000,000 135,000,000 65,000,000 140,000,000 200,000,000 70,000,000 175,000,000 120,000,000 90,000,000 90,000,000 550,000,000 380,000,000 130,000,000 385,000,000 465,000,000 365,000,000 450,000,000 95,000,000 202,500,000 190,000,000 290,000,000 360,000,000 177,500,000 365,000,000 515,000,000 550,000,000 460,000,000 315,000,000 240,000,000 240,000,000 499356 2,445,000,000 2,620,000,000 1,660,000,000 6,725,000,000 110,000,000 75,000,000 25,000,000 75,000,000 90,000,000 75,000,000 90,000,000 25,000,000 42,500,000 40,000,000 60,000,000 75,000,000 37,500,000 75,000,000 105,000,000 400,000,000 95,000,000 65,000,000 50,000,000 50,000,000 220,000,000 155,000,000 55,000,000 160,000,000 190,000,000 150,000,000 185,000,000 35,000,000 85,000,000 80,000,000 120,000,000 150,000,000 75,000,000 150,000,000 210,000,000 80,000,000 190,000,000 130,000,000 100,000,000 100,000,000 | 52969 | 51
355 | Kapiri Mposhi Central Serenge Mambwe Eastern Kawambwa Luapula Mpika Nothern Mungwi | 54205 | 51 | Mambwe, Kawambwa, Mpika, Mungwi
356 | Mporokoso Noth/Western Chavuma Kabompo Kasempa Mufumbwe | 54300 | 51 | Chavuma, Kabompo, Kasempa, Mufumbwe, Mporokoso
357 | Mwinilunga Zambezi Kalabo Western Kaoma Lukulu Mongu | 54362 | 51 | Lunga, Mwinilunga, Zambezi, Kalabo, Kaoma, Lukulu, Mongu
358 | Senanga Shesheke Shangombo Total | 54423 | 51 | Senanga
359 | Table 17: Social Protection Implementation Schedule 2009 - 2010 | 54461 | 52
360 | Mon Mon Mon Mon Mon Mon Mon Mon Mon 1 2 3 4 5 6 7 8 9 Mon 10 Mon 11 Mon 12 Months | 54530 | 52
361 | 45 | 54638 | 52
362 | Activity Raising Awareness Training of Stakeholders and Children Delivery Of materials Equip Service Delivery Centers Formation of Protection Community Committees | 54643 | 52 |  | War, rain
363 | Monitoring of Protection Activities | 54820 | 52
364 | Annex 7: WATER AND SANITATION | 54859 | 53 |  | water
365 | Problem Statement and Rationale | 54894 | 53
366 | During the 2008/9 floods, most of the water points (especially unprotected shallow wells) were submerged and some of the walls collapsed. Despite most of the water points being submerged, people have continued to use the same sources because they lack alternative sources. Therefore it is necessary that the damaged water facilities are urgently rehabilitated. Furthermore, the affected communities should be sensitized on water treatment and proper hygiene practices and also provided with chlorine. | 54928 | 53 |  | water, water, water, water, flood | 2008/9
367 | Activities The sector will address household level and community water safety and awareness raising on improved sanitary disposal and hygiene practices. The mitigation measures for Water & Sanitation are as shown in the table below. | 55437 | 53 |  | water, water, War |  | household
368 | SECTOR Water and sanitation infrastructure (rehabilitation (boreholes) and sanitation and ACTIVITY Water and Sanitation Provision of safe water to affected communities (Household Chlorine, HTH Chlorine) Provision of water (latrines) sinking/digging of new ones) Provision of water storage containers, soap and hand washing facilities. Improvement of water sources Training: Hygiene promoters and V-WASHE committees Water quality & quantity monitoring, proper usage of home chlorination and HTH, management of water and sanitation facilities and safe excreta disposal. Proper garbage handling and disposal Monitoring and Evaluation | 55675 | 53 |  | water, water, water, water, water, water, water, water, rain |  | household, home
369 | The activities will include supply of chlorine for treatment of domestic water, granular chlorine for communal water sources and strengthening community sensitization programmes on public health and hygiene, drilling and rehabilitation | 56331 | 53 |  | water, water
370 | of water facilities to ensure access to safe drinking water and promotion of construction of adequate sanitary facilities. | 56571 | 54 |  | water, water
371 | Implementing Agencies | 56700 | 54
372 | • Ministry of Local Government and Housing • Ministry of Energy and Water Development • Cooperating Partners • Private Sector • Non Governmental Organizations | 56724 | 54 |  | water
373 | Financial Requirements: ZMK 8,379,843,031(US$1,675,968.61) | 56889 | 54
374 | 47 Table 18: Water and Sanitation Activity Budget and Schedule 2009 – 2010 (Requirements by District) | 56950 | 55 |  | water | 2009, 2010
375 | Water Sanitation Water Quality Boreholes with handpumps Total Cost 10% of need Ordinary Pit Latrines 10% of need Total Cost Chlorin Chlorine e cost (bottle (K1000/bo s) ttle) Granular Chlorine (HTH) (50Kg) HTH cost (K800,000 /50Kg) 20litre Containe Container cost (K20,000/cont rs ) | 57058 | 55 |  | water, water
376 | 4 2 2 3 9 6 5 2 1 2 2 6 3,034,400 5690 85,342,500 | 57371 | 55
377 | 1,711,733 3210 48,142,500 1,218,133 2284 34,260,000 2,734,133 5127 76,897,500 6,841,067 12827 192,405,000 4,842,400 9080 136,192,500 4,390,933 8233 123,495,000 1,339,467 2512 37,672,500 530,667 995 14,925,000 1,275,200 2391 35,865,000 1,289,867 2419 36,277,500 4,468,533 8379 125,677,500 | 57437 | 55
378 | l a r t n e C | 57759 | 55
379 | n r e t s a E a l u p a u L | 57774 | 55
380 | n r e h t r o N | 57803 | 55
381 | n r e t s e W h t r o N | 57820 | 55
382 | Affected Populati on 11,379 6,419 Kapiri Mposhi Serenje Mambwe 4,568 Kawambwa 10,253 5 3 2 4 136,548,000 190 94,825,000 3,793 3,793,000 77,028,000 107 53,491,667 2,140 2,139,667 | 57845 | 55 | Serenje, Mambwe, Kawambwa
383 | 54,816,000 76 38,066,667 1,523 1,522,667 123,036,000 171 85,441,667 3,418 3,417,667 Mporokoso 25,654 10 307,848,000 428 213,783,333 8,551 8,551,333 Mpika 18,159 Mungwi 16,466 Mufumbwe 5,023 Kasempa 1,990 Kabompo 4,782 Chavuma 4,837 Mwinilunga 16,757 7 7 2 1 2 2 7 217,908,000 303 151,325,000 6,053 6,053,000 197,592,000 274 137,216,667 5,489 5,488,667 60,276,000 23,880,000 57,384,000 58,044,000 84 33 80 81 41,858,333 1,674 1,674,333 16,583,333 663 663,333 39,850,000 1,594 1,594,000 40,308,333 1,612 1,612,333 201,084,000 279 139,641,667 5,586 5,585,667 | 58049 | 55 | Lunga, Mpika, Chavuma, Kabompo, Kasempa, Mufumbwe, Mwinilunga, Mporokoso, Mungwi
384 | 48 | 58680 | 56
385 | Water Sanitation Water Quality Affected Populati on 12,570 | 58688 | 56 |  | water, water
386 | Zambezi | 58754 | 56 | Zambezi
387 | n r e t s e W Kaoma 13,178 Kalabo 22,592 Lukulu 8,091 Mongu 13,360 Senanga 17,438 Sesheke 9,809 Shang’omb o 15,122 Boreholes with handpumps Total Cost 10% of need 5 150,840,000 Ordinary Pit Latrines 10% of need 210 Total Cost Chlorin Chlorine e cost (bottle (K1000/bo s) ttle) Granular Chlorine (HTH) (50Kg) HTH cost (K800,000 /50Kg) 20litre Containe Container cost (K20,000/cont rs ) 104,750,000 4,190 4,190,000 4 3,352,000 6285 94,275,000 5 9 3 5 7 4 6 158,136,000 220 109,816,667 4,393 | 58764 | 56 | Kalabo, Kaoma, Lukulu, Mongu, Senanga, Sesheke
388 | 4,392,667 | 59314 | 56
389 | 271,104,000 377 188,266,667 7,531 7,530,667 | 59326 | 56
390 | 97,092,000 135 67,425,000 2,697 2,697,000 160,320,000 223 111,333,333 4,453 4,453,333 209,256,000 291 145,316,667 5,813 5,812,667 | 59376 | 56
391 | 117,708,000 163 81,741,667 3,270 3,269,667 | 59522 | 56
392 | 181,464,000 252 126,016,667 5,041 5,040,667 4 8 3 4 6 3 5 | 59571 | 56
393 | 3,514,133 6589 98,835,000 | 59642 | 56
394 | 6,024,533 11296 169,440,000 | 59672 | 56
395 | 2,157,600 4046 60,682,500 | 59704 | 56
396 | 3,562,667 6680 100,200,000 | 59734 | 56
397 | 4,650,133 8719 130,785,000 | 59765 | 56
398 | 2,615,733 4905 73,567,500 | 59796 | 56
399 | 4,032,533 7561 113,415,000 Total | 59826 | 56
400 | Grand Total 238,447 95 2,861,364,000 3,974 1,987,058,333 79,482 79,482,333 79 63,585,865 119,224 1,788,352,500 6,779,843,031.00 | 59864 | 56
401 | 49 Cost | 60006 | 57
402 | Additional Budget Activity Rehabilitation of water infrastructure Rehabilitation of sanitation infrastructure Training and Sensitization Monitoring and Evaluation Total The estimated Total Budget for Water and Sanitation for the period (July 2009 to June 2010) is ZMK 8,379,843,031 Note: The estimate for chlorine is for 1 month only thereafter it is hoped that the households will be able to buy the chlorine on their own. 1,000,000,000 300,000,000 200,000,000 100,000,000 1,600,000,000 | 60020 | 57 |  | water, water, rain |  | household, households
403 | 50 | 60524 | 58
404 | Table 19: Water and Sanitation Activity Schedule | 60532 | 58 |  | water
405 | S/N Activity month month month month month month month month month month month month 1 2 3 4 5 6 7 8 9 10 11 12 Time Frame 1 Training of V-WASHE 2 Training of hygiene Promoters 3 4 5 Delivery of Materials (containers, chlorine) Chlorine promotion sensitization Construction and equipping of boreholes 6 Construction of Pit Latrines Rehabilitation of water and sanitation facilities 7 8 Monitoring and Evaluation | 60583 | 58 |  | water, rain, rain
406 | 51 Annex: 8: AGRICULTURE AND FOOD SECURITY AGRICULTURE Problem statement and rationale The country has continued to be negatively impacted by floods in the past three rain seasons. Every year the plains flood to some extent, but in late February and first half of March 2009, the extent of floods exceeded the highest water levels ever recorded. The above normal rains season received led to flooding that left a trail of destruction of field crops, infrastructure and thousands of people and livestock were displaced. Though the in-depth assessment show a marginal increase in crop production at household level, these household have been hit by floods for three consecutive seasons. This means that their production might not sustain them up to the next season hence the need to supplement their household food security through off season crop production. | 61039 | 59 |  | water, flood, flood, flood, flood, flood, rain, rain |  | household, household, household
407 | Floods and/or water logging have exposed the affected population to the risk of outbreak of waterborne diseases and increased the likelihood of animal disease incidences. The damage to crops has contributed to food insecurity problems in some the affected districts. Over the years floods have become a major development challenge because they tend to reverse the development process and livelihood recoveries in the various sectors particularly in agriculture where household asset base have continued to be eroded. Consequently the recovery process have to start all over again, begging for fresh interventions and infrastructure development and rehabilitation. In order to mitigate the impact of the floods, government will need to | 61916 | 59 |  | disease, disease, water, water, disease, disease, disease, disease, flood, flood, flood |  | household
408 | 52 implement short to medium and long-term interventions in all the sectors identified to have been affected. | 62662 | 60
409 | ACTIVITIES The activities will address food insecurity and its related consequences such as malnutrition, morbidity and mortality. In terms of focus, the activities will cover off season crop production and animal health. The required interventions are as summarized in the activity matrix (Refer to table 20 below). | 62779 | 60
410 | Implementing Agency: MACO, MCDSS, PAM, FAO | 63103 | 60
411 | Financial Requirements: ZMK 5,662,747,143(US$ 1,132,549.43) | 63148 | 60
412 | 53 | 63210 | 61
413 | Table 20: Agriculture Activity Schedule | 63218 | 61
414 | Activity Resources required Resources available | 63260 | 61
415 | Dry season crop production input support | 63314 | 61
416 | GAP | 63358 | 61
417 | Fertiliser Seed 4,445,060,000 | 63364 | 61
418 | 4,445,060,000 761,830,000 | 63398 | 61
419 | 761,830,000 | 63427 | 61
420 | livestock disease vaccination 500,000,000 387,000,000 113,000,000 Livestock dipping 600,000,000 257,142,857 342,857,143 | 63441 | 61 |  | disease, disease, disease
421 | Total 6,306,890,000 644142857 5,662,747,143 Time frame Comment July August Sept Oct Nov Dec | 63570 | 61
422 | 54 Table 21: Estimated Input Requirements to Enable Targeted Households cultivate 1 Lima of Maize for Off Season Crop production | 63670 | 62 |  |  |  | household, households
423 | The Bank of Zambia Foreign Exchange rate used in this document is US$ 1 = ZMK 5, 000. Note: The column of total requirement represents the actual gap (available resources already considered before arriving at the gap) | 63806 | 62
424 | Name of District Chavuma Chiyeke Kakoma Kalombo Kamusamba Kambuya Mukelangombe Kanyinda Likundu Nguvu Nyantanda Nyambingila Zambezi Mpidi Kakonga Likungu Mapachi Chinyingi Matondo Nyachikanji Muyembe Liyoyu Mwange Nyawanda Mwinilunga Nthambu Kamapanga Chana Chamuhinga Kanyama | 64027 | 62 | Lunga, Chavuma, Mwinilunga, Zambezi
425 | Pop 2008 Est HHs# HHs targeted 30% Area (Ha) Seed (MT) @20Kg/Ha D comp (MT)@.2MT/Ha Urea (MT) @.2MT/Ha Seed cost @ 1600 U$/MT D Comp@ U$ 877/MT Urea @ U$ 877/MT | 64325 | 62 |  |  | 2008
426 | 7,270 4,247 1,395 911 1,161 2,475 6,930 3,013 8,435 3,991 5,790 2,599 9442 8,929 3,708 10,814 | 64508 | 62
427 | 1,212 708 233 152 194 413 1,155 502 1,406 665 965 433 1,574 1,488 618 1,802 | 64619 | 62
428 | 364 212 70 46 58 743 | 64712 | 62
429 | 347 151 422 200 290 130 | 64740 | 62
430 | 472 446 185 541 | 64771 | 62
431 | 91 53 17 11 15 186 87 38 105 50 72 32 118 112 46 135 | 64792 | 62
432 | 1.818 1.062 0.349 0.228 0.290 3.713 | 64862 | 62
433 | 1.733 0.753 2.109 0.998 1.448 0.650 | 64905 | 62
434 | 2.361 2.232 0.927 2.704 | 64948 | 62
435 | 18.2 10.6 3.5 2.3 2.9 37.1 | 64977 | 62
436 | 17.3 7.5 21.1 10.0 14.5 6.5 | 65011 | 62
437 | 23.6 22.3 9.3 27.0 | 65046 | 62
438 | 18.2 10.6 3.5 2.3 2.9 37.1 | 65070 | 62
439 | 17.3 7.5 21.1 10.0 14.5 6.5 | 65104 | 62
440 | 23.6 22.3 9.3 27.0 | 65139 | 62
441 | 2,908 1,699 558 364 464 5,940 11,934 2,772 1,205 3,374 1,596 2,316 1,040 12,303 3,777 3,572 1,483 4,326 13,157 | 65163 | 62
442 | 15,939 9,312 3,059 1,997 2,545 32,559 65,411 15,194 6,606 18,494 8,750 12,695 5,698 67,437 20,702 19,577 8,130 23,710 72,118 | 65294 | 62
443 | 15,939 9,312 3,059 1,997 2,545 32,559 65,411 15,194 6,606 18,494 8,750 12,695 5,698 67,437 20,702 19,577 8,130 23,710 72,118 55 Name of District Pop 2008 Est HHs# HHs targeted 30% Area (Ha) | 65439 | 63 |  |  | 2008
444 | Lukulu Mbanga Mwito Kang'oti Dongwe Kawaya Kashizhi Lutembwe Mitete Nyaala Mwandi Likapai Luanchuama Matala Senanga Lyamakamba Silowana Shekela Makoka Kambayi Kataba Muoyo Nangucha Mwana Mbuya Imatongo Imatanda Wanyau Lipuwe Naluywa Lumbe Sibuli Maata | 65660 | 63 | Lukulu, Mitete, Mwandi, Senanga
445 | 4,818 6,653 4,711 2,573 2,357 6,042 2,666 3,580 6,418 2,760 699 1,500 395 5,155 7,443 1,353 1,353 1,353 1,353 1,353 1,353 1,353 5,757 1,353 1,353 1,324 1,353 1,353 1,324 1,353 803 1,109 785 429 393 1,007 444 597 1,070 460 117 250 66 859 1,241 226 226 226 226 226 226 226 960 226 226 221 226 226 221 226 | 65945 | 63
446 | 241 333 236 129 118 302 133 179 321 138 35 75 20 | 66309 | 63
447 | 258 372 68 68 68 68 68 68 68 288 68 68 66 68 68 66 68 60 83 59 32 29 76 33 45 80 35 9 19 5 64 93 17 17 17 17 17 17 17 72 17 17 17 17 17 17 17 Seed (MT) @20Kg/Ha D comp (MT)@.2MT/Ha Urea (MT) @.2MT/Ha | 66372 | 63
448 | 1.205 1.663 1.178 0.643 0.589 1.511 0.667 0.895 1.605 0.690 0.175 0.375 0.099 | 66626 | 63
449 | 1.289 1.861 0.338 0.338 0.338 0.338 0.338 0.338 0.338 1.439 0.338 0.338 0.331 0.338 0.338 0.331 0.338 | 66718 | 63
450 | 12.0 16.6 11.8 6.4 5.9 15.1 6.7 9.0 16.0 6.9 1.7 3.8 1.0 | 66838 | 63
451 | 12.9 18.6 3.4 3.4 3.4 3.4 3.4 3.4 3.4 14.4 3.4 3.4 3.3 3.4 3.4 3.3 3.4 | 66909 | 63
452 | 12.0 16.6 11.8 6.4 5.9 15.1 6.7 9.0 16.0 6.9 1.7 3.8 1.0 | 66998 | 63
453 | 12.9 18.6 3.4 3.4 3.4 3.4 3.4 3.4 3.4 14.4 3.4 3.4 3.3 3.4 3.4 3.3 3.4 | 67069 | 63
454 | Seed cost @ 1600 U$/MT | 67158 | 63
455 | D Comp@ U$ 877/MT | 67184 | 63
456 | Urea @ U$ 877/MT | 67205 | 63
457 | 1,927 2,661 1,884 1,029 943 2,417 1,066 1,432 2,567 1,104 280 600 158 18,069 | 67225 | 63
458 | 2,062 2,977 541 541 541 541 541 541 541 2,303 541 541 530 541 541 530 541 14,896 10,563 14,587 10,329 5,641 5,168 13,247 5,845 7,849 14,071 6,051 1,533 3,289 866 99,040 11,302 16,319 2,966 2,966 2,966 2,966 2,966 2,966 2,966 12,622 2,966 2,966 2,903 2,966 2,966 2,903 2,966 81,647 10,563 14,587 10,329 5,641 5,168 13,247 5,845 7,849 14,071 6,051 1,533 3,289 866 99,040 11,302 16,319 2,966 2,966 2,966 2,966 2,966 2,966 2,966 12,622 2,966 2,966 2,903 2,966 2,966 2,903 2,966 81,647 | 67317 | 63
459 | 56 Name of District Pop 2008 Est HHs# HHs targeted 30% Area (Ha) Seed (MT) @20Kg/Ha D comp (MT)@.2MT/Ha Urea (MT) @.2MT/Ha Seed cost @ 1600 U$/MT D Comp@ U$ 877/MT Urea @ U$ 877/MT Mongu Mbekise Nakanya Imalyo Ndanda Nakato Yeta Katongo Mabungu Mabili Lealui Lumbo Kama Namengo Limulunga Nang'oko Ushaa Namushakende Total TOTAL | 67881 | 64 | Lunga, Limulunga, Mongu |  | 2008
460 | 1,214 1,938 1,307 3,310 1347 1,941 2,118 958 533 2,474 1,743 1,456 1,456 2,975 1,456 1,493 1,405 | 68253 | 64
461 | 202 323 218 552 224.5 324 353 160 89 412 291 243 243 496 243 249 234 61 97 65 166 67.35 97 106 48 27 124 87 73 73 149 73 75 70 15 24 16 41 16.8 24 26 12 7 31 22 18 18 37 18 19 18 | 68368 | 64
462 | 0.304 0.485 0.327 0.828 0.337 0.485 0.530 0.240 0.133 0.619 0.436 0.364 0.364 0.744 0.364 0.373 0.351 51.26 51 MT | 68599 | 64
463 | 3.0 4.8 3.3 8.3 3.4 4.9 5.3 2.4 1.3 6.2 4.4 3.6 3.6 7.4 3.6 3.7 3.5 512.6 506 MT | 68733 | 64
464 | 3.0 4.8 3.3 8.3 3.4 4.9 5.3 2.4 1.3 6.2 4.4 3.6 3.6 7.4 3.6 3.7 3.5 512.6 506 MT | 68834 | 64
465 | 486 775 523 1,324 539 776 847 383 213 990 697 582 582 1,190 582 597 562 82,008 152,366 2,662 4,249 2,866 7,257 2,953 4,256 4,644 2,100 1,169 5,424 3,822 3,192 3,192 6,523 3,192 3,273 3,080 63,854 449,506 2,662 4,249 2,866 7,257 2,953 4,256 4,644 2,100 1,169 5,424 3,822 3,192 3,192 6,523 3,192 3,273 3,080 63,854 449,506 | 68935 | 64
466 | Cost of Transportation ZMK 1,051,380,000.00 (US$ 210,276) TOTAL COST OFOFF SEASON CROP PRODUCTION PROGRAMME ZMK 5,206,890,000.00 (US$ 1,041,378.00) Notes: The two provinces require early maturing maize seed varieties: • Option 1. Preferred DACOs - MMV 441, or SC 504, SC 514 • Option 2. Sustainability considerations especially under low fertilizer availability; ZM 421 or ZM 521, i.e. low Nitrogen requirement varieties Early delivery of inputs separates success or failure High operational support costs for input delivery in Western and NW provinces | 69314 | 64
467 | 57 RELIEF FOOD Problem Statement and Rationale The floods of 2008/09 season have had a negative impact on the lives of affected communities. According to the In- depth Vulnerability and Needs Assessment on the impact of floods and/or prolonged dry spells conducted by the VAC in 2009, heavy rains and floods have severely affected small scale farmers’ crops in 7 districts namely; Chavuma, Kabompo, Mporokoso, Mungwi, Mwinilunga, Serenje and Zambezi. | 69877 | 65 | Serenje, Lunga, Chavuma, Kabompo, Mwinilunga, Zambezi, Mporokoso, Mungwi | flood, flood, flood, rain | of 2008/09, 2009
468 | Considering the negative impact of excessive rains and floods on the seven districts, there is need to urgently address the resultant problems with specific interventions that will mitigate the effects of loss of crops, food and assets of the affected households. Interventions that include relief food, provision of agricultural inputs and vaccinating livestock will help address the core problems in the short, medium to long term. | 70341 | 65 |  | agricultural, flood, rain |  | household, households
469 | Activities The following three activities should be undertaken to mitigate the negative impact of heavy rains and floods on food security in the severely affected districts mentioned above. These activities are procurement, transportation and distribution of relief food | 70782 | 65 |  | flood, rain
470 | Target A total of 110, 651 people (18,442 households) in seven (7) affected districts mentioned above will be targeted for relief food amounting to 8,295.5 MTs. | 71059 | 65 |  |  |  | household, households
471 | Implementing Agencies Office of the Vice President as well as relevant NGOs and cooperating partners. | 71224 | 65 |  |  |  | resident
472 | 58 Financial Requirements A total of K17, 143,190,104.00(US$3,428,638.02) will be needed to implement the activities as reflected in the activity matrix below: | 71329 | 66
473 | Table 22: Food Relief Activity Matrix | 71497 | 66
474 | ACTIVITY RESOURCE REQUIREMENT RESOURCES AVAILABLE GAP (ZmK) (ZmK) (ZmK) 1. Procurement of 8,295.5 MTs of Relief food 2.Transportation of 8,295.5 MTs of Relief food 3. Distribution of 8,295.5 MTs of Relief of food 10,784,124,000.00 | 71537 | 66
475 | 2,657,208,154.00 | 71788 | 66
476 | 3,701,857,950.00 | 71807 | 66
477 | 17,143,190,104.00 0 10,784,124,000.00 | 71826 | 66
478 | 0 2,657,208,154.00 | 71867 | 66
479 | 0 | 71888 | 66
480 | 3,701,857,950.00 | 71892 | 66
481 | 17,143,190,104.00 Sector Total | 71911 | 66
482 | Total Cost Under Agriculture And Food Security: ZMK 22,805,937,247.00 (US$4,561,187.45 | 71945 | 66
483 | 59 | 72035 | 67